## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Duan Lin
Lead Roles: Team Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 10 | 9 | 1 | 0 - learn Flask and MongoDB documentations, go over tutorials 5 - assign tasks to subteams, actively send reminders to backend members 6 - set up git, clone remote repo, create new commit and successfully push to branch "lab1" | 7 | 1 | [6 empty] | 1. Collaborate requirement leader write 3 sections of SPPP 2. Take meeting minutes and assign required tasks to backend members. 3. Set up git, commit a test message on git | 1. not familar with DB connection with Flask framework | 1. Learn tutorials online and do some demo coding work. 2. Send task assignments to all members again | 0 - continue to learn Flask and backend part 2 - start design user schemes 3 - implement some functions such as user registration, user login and verify user's password | 10
2 | 09/14-09/20 | 13 | 11 | 1 | 0 - learn Flask and MongoDB 1 - carefully analyze the feasibility of requirements 2 - design dairy database and user info collections in MongoDB | 5 | 1 | 5
3 | 09/21 - 09/27 | 14.5 | 10.5 | 4 | 0 - learn Flask and MongoDB 2 - design user info collections with type verification 3 - implement three routes: login, register, search 4 - test the register and login functions, successfully add new record into user info collections 5 - Hold Back-End group meeting before our presentation, actively communicate with teammates on payment security design. 5 - Remind team members to fill out SPPP documents and assign tasks for Iteration0 presentation | 3 |  | 1 | 5 | 1.5 |  | 4
4 | 09/28 - 10/3 | 6 | 5 | 1 | 0 - learn Flask and MongoDB 2 - design user info collections with type verification 5 - Hold Back-End group meeting and weekly meeting, focus on new feature design | 3 |  | 2 |  |  | 1
5 | 10/4 - 10/10 | 10 | 8 | 2 | 0 - learn Flask and MongoDB 2 - design user info collections with type verification 4 - test the register and login functions, successfully add new record into user info collections 5 - Hold meetings with team members
6 | 10/11 - 10/17 | 18 | 17 | 1 | 3 - design register rules, including password null field detect and many format restriction. 4 - test the register and login functions, successfully add new record into user info collections 4 - test different rules in user registration, write test cases. 5 - Hold meetings with team members
7 | 10/18 - 10/24 | 12 | 11 | 1 | 1 - assign new requirement: Google login 3 - design register and login rules 3 - integrate front-end pages in Flask project, making HTML and CSS works. 4 - test the register and login functions, successfully add new record into user info collections 4 - test on manual sign up and login, google login and product pages. 5 - Hold meetings with team members. 6 - Install OAuth and third-party library in Flask. |  | 0.5 |  | 4 | 3 | 1 | 0.5 |  | - Finished manual user registration and login - Finished front-end integration with Shuyi Zheng - Designed rules for user registration. - Assign Google Login function design to backend team - Update team works before iteration 1 presentation | - Integrated with html and css | - move html and css into /template and /static folder

## Ming Yuan
Lead Roles: Team Leader, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 6 | 5 | 1 | 0 - learn basic soft engineering concepts(module 1-2) 5 - communicate with teammates on the team meeting" | 5 | [7 empty] | 1. Collaborate requirement leader write 3 sections of SPPP 2. Take meeting minutes and assign required tasks to backend members. 3. Set up git, commit a test message on git | 1. not familar with DB connection with Flask framework | 1. Learn tutorials online and do some demo coding work. 2. Send task assignments to all members again | 0 - continue to learn Flask and backend part 2 - start design user schemes 3 - implement some functions such as user registration, user login and verify user's password | 10
2 | 09/14-09/20 | 8 | 7 | 1 | 0 - learn modules 3-4 on the blackboard 6 - set up the git and use GitHub Desktop to complete the lab1 | 7
3 | 09/21 -09/27 | 10 | 6 | 4 | 0 - learn module 5-6 on the blackboard 0 - learn flask and mongoDB with python 5 - weekly team meeting. 5 - discuss with my back-end subteam about back-end implentation plan. | 6 |  |  |  |  | 4
4 | 09/28 - 10/4 | 6 | 4 | 2 | 0 - learn soft engineering software security framwork 5 - Discuss with teammates with implementation, security part and work division | 4 |  |  |  |  | 2
5 | 10/5 - 10/11 | 7 | 6 | 1 | 0 - learn Flask and Miscrosoft SDL 2 - design for security of user registration and login 5 - Meet with teammates talking about the functionality of iteration 1 | 2 |  | 3 |  |  | 2
6 | 10/12 - 10/18 | 8 | 7 | 1 | 3 - work with team leader to complete the code to realize the user registration and login 4 - test the functionality of registration and login 7 - think over possible security issues with our functionality already completed | 2 |  |  | 4 | 2 |  |  | 2

## Shreyas Prakash
Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/09-09/13 | 10 | 9 | 1 | 0 - Learning Flask, MongoDB and API integration with front end 1- Analyzing the functional and non functional requirements for the appication 2- Came up with low level design for the appication and discussed with team members 6 - Clone Remote Git Repository, Created the commit and pushed to the branch "lab1" | 9 | 0.2 | 0.5 |  |  |  | 0.3 |  | Came up with Low level design for the complete application and had a discussion with the team | Which Database to use? How to configure the product Information? File Format? How do we pre populate the product information into product DB? | Which Database to use? As we want our Application to give accurate results which means consistency is given priority over Availabilty(comparitively) and also our application should be Partition Tolerent we decided to go with MongoDB. How to configure the product Information? File Format? File format is YAML files as it easily readable format and can be parsed into JSON representation later How do we pre populate the product information into product DB? Auto Integrating the product DB with YAML parser. | Analyze the DB partitioning techniques and YAML Configuration and integrating with MongoDB. Discuss about functional and Non funcitonal required and make note of API functionalities for the application. Start Implementing Initial Route and integrae with Product DB and front end HTML files and check if we are able to store user details in the given JSON format into MongoDB | 10
2 | 09/14-09/20 | 13 | 11 | 2 | 0 - Learning Flask integration with front end using Jinja2. Learning about YAML configuration and how to populate the MongoDB with JSON files. 2 - Came up with the database partitioning technique and page links which had to be taken care in the high level design. 3 - Started Implementing the Initial Route using Flask and integrated with the HTML pages designed by front end team. 5 - Communicated with the front end team to discuss about the dynamic content creation using Jinja2 by parsing JSON data. | 6 |  | 1 | 4 |  | 2 |  |  | Came up with Database partitioning technique based on the functionalities and load traffic. Created the Initiate route for our Application and integrated with MongoDB and front end HTML pages. | Problem with Integrating the route with front end HTML pages and dynamic content creation. JSON representation of the orders that have been placed by a single individual | Problem with Integrating the route with front end HTML pages and dynamic content creation. Worked Collaboratively with front end team to learn in depth about Jinja2 framework for dynamic content creation(gave the logic for the dynamic content creation) Finalized the JSON representation for faster performance of the application by using Nested JSON format. | Finalize the High level Design and trade offs. Implement complete end to end working of the application for creating user profiles and adding the user profiles to the MongoDB. Come up with functionality logic and format for product information. | 13
3 | 09/21-09/24 | 12 | 9 | 2 | 0- Learning aggregation of JSON data and auto integration of JSON data into MongoDB. 2- Came up with the high level design of the complete application which includes all sharding mechanisms and trade offs. 3- Implemented product information functionality and auto integrated results with MongoDB & passed the results to front end team to make dynamic content. 5- Communicated with front end team on the JSON results that were passed and worked collaboratively in creating dynamic content. | 7 |  | 1.5 | 2 |  | 1.5 |  |  | Came up with the finalized High level Design. Discussed with team members for any trade offs. Implemented product information functionality and auto integrated the JSON results with MongoDB. Communicated with frond end team for dynamic content creation for the JSON data that was parsed. | Should we render the HTML files within the same route or different routes? How do we handle multiple requests at the same time? | Should we render the HTML files within the same route or different routes?How do we handle multiple requests at the same time? So the basic idea was to render the HTML files inside the same route under POST method as this can give us an interface which will have access to all the products that have been selected by the user. So this way we can even handle multiple request through form.get() method and store values in List and processing the information throught the list elements. | Check for the end to end flow for the multiple requests( Multiple Product information at single point of time) Start implementing the product selection functionality keeping in mind about the multiple requests. Work collaboratively with frond end team to get done with Dynamic access content for the JSON parsed. | 12
4 | 09/25-10/02 | 11 | 9 | 2 | 0- Learning about integrating API's with front end and design patterns which are required for API Design 2- Designed an architecture that helps us to integrate Google API with our API's and get dynamic access. 3- Implemented a parser which converts YAML files into JSON and dynamically store them on MongoDB. 4- Communicated with front end team for giving better approach for Dynamic content creation upon receiving JSON data. Attended weekly sync ups. | 6 |  | 1 | 1 |  | 1 |  |  | Creation of Config YAML files for products storing them on MongoDB dynamicaly |  |  |  | 11
5 | 10/03-10/09 | 10 | 7 | 3 | 0 - Learning to Integrate Google API with our API's 3- Implemented '/login' route which will use Google API to get access for Email ID's and integrated with front end HTML page which renders this route. 4- Tested if all Config files which are parsed into JSON and placed on MongoDB are correct and does not contain duplicate items. 5- Collaborated with team members on meetings and started preparation for Iteration-1 | 4 |  |  | 1.5 | 1.5 | 3 |  |  | Implemented Initial Route for Google API along with other back end team members and integrated with HTML page that renders this route for Gmail access. |  |  |  | 10
6 | 10/10-10/17 | 12 | 10 | 2 | 0- Learning to Integrate Google Sign up and also learning the end point on where is the end point in Google API design when we get a confirmation that Email ID is verified. 2- Designed the End to End architecture for retrieving prouduct information from the MongoDB collection and send it to the front end dynamically producing the product information on the front end. 3- Implemented a method to integrate the '/login' route with '/authrorize'. Successfully wrote a method to that uses Google API and verifies the Gmail ID's to allow user to enter the application. 5- Collaborated with team members on meetings and continued the preparation for Iteration-1 | 7 |  | 1 | 2 |  | 2 |  |  | Implemented a method to integrate the '/login' route with '/authrorize'. Successfully wrote a method to that uses Google API and verifies the Gmail ID's to allow user to enter the application. |  |  |  | 12
7 | 10/18-10/22 | 26 | 23 | 3 | 0- Learnt to integrate all the components that had been developed by now so that everything is working when integrated(front end, API and backend work) 2- Successfully Designed and End to End architecture to connect all the components of front end work, API Design and back end work. 3- Implemented the complete integration of Front end HTML pages, Google API's along with the API's that we have created and the MongoDB and made sure everything is working properly from end to end in our application. 5- Collaborated with team members on meetings and made sure we have prepared everything that is necessary for Iteration-1. | 6 |  | 1 | 16 |  | 3 |  |  | Implemented the complete integration of Front end HTML pages, Google API's along with the API's that we have created and the MongoDB and made sure everything is working properly from end to end in our application. |  |  |  | 15

## Neha Jadhav Sarnaik
Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 11 | 9 | 0 | 0 - Learn Flask, MongoDB and API integration with front end 1- Research on the requirements for the appication 2- Discussed about low level design with team members | 9 | 1 | 1 | [9 empty] | 11
2 | 09/14-09/20 | 15 | 11 | 1 | 0 - Learn Flask ,API integration with front end ,MongoDB 3 - Started Implementing the Initial Route using Flask and integrated with the HTML pages developed by the front end team. 5 - Communicated with the front end team to discuss about the dynamic content creation using Jinja2 .6 - Clone Remote Git Repository, Created the commit and pushed to the branch lab1 | 8 |  |  | 4 |  | 2 | 1 | [5 empty] | 13
3 | 09/21-09/24 | 9 | 8 | 1 | 0- Learning aggregation of JSON data and integration in MongoDB 2- Analyzed of how the high level design will be of the complete application . 5- Communicated with backend team on how the application will work and discussed the high level design with the team. | 6 |  | 2 |  |  | 1 | [6 empty] | 12
4 | 09/25 - 10/02 | 12 | 11 | 1 | 2-Created the authorization code stream utilizing google login 3- Began with implementation part somewhat 5 - Colaberated with team members on working of the application |  |  | 6 | 5 |  | 1
5 | 10/03 - 10/10 | 14 | 13 | 1 | 3 - Executed google login for the application 4 - test the google login 5 - colaborated with team members to discuss about the iteration 1 |  |  |  | 7 | 5 | 1
6 | 10/11 - 10/18 |  |  |  | 5- Coordinated with team members on meetings and continued the prepare for Iteration-1

## Shuyi Zheng
Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/07-09/13 | 2.5 | 1.5 | 1 | 0 - learn git 1 - organize requirements 5 - finish weekly MeetingMinutes | 0.5 | 0.5 |  |  |  | 0.5 |  |  | 1. write functional requirement |  |  | 0 - start to learn web design 1 - continue to define requirements 2 - finish UI design 2 - start web design | 10
2 | 09/14-09/20 | 16 | 15 | 1 | 0 - learn adobe xd 2 - UI design 2 - logo design 3 - implementation 5 - make project plan | 1 |  | 6.5 | 7.5 |  |  |  |  | 1. finish logo design 2. finish UI design 3. homepage development | 1. not familar with UI design software 2. not familar with HTML, CSS | 1. finish Adobe XD tutorial in one day, finish Design 2. finish HTML tutorial in one day, be able to write HTML | 0 - continue to learn CSS HTML 1 - continue to define requirement 3 - implement homepage | 10
3 | 09/21-09/27 | 4 | 2 | 2 | 7 - prepare presentation | 2 | [6 empty] | 2 | 1. participate in iteration 0 presentation 2. learn html layout |  |  | 3 - implement homepage | 8
4 | 09/28-10/04 | 2 | 1 | 1 | 0 - learn css | 1 | [6 empty] | 1 | 1. start with homepage |  |  | 3 - implement homepage | 8
5 | 10/05-10/11 | 7.5 | 6.5 | 1 | 0 - learn css/html 3 - implement homepage |  |  |  | 6.5 |  |  |  | 1 | 1. finish homepage |  |  | 3 - implement login page | 8
6 | 10/12-10/18 | 13 | 11 | 2 | 0 - learn css/html 3 - implement login page 3 - implement register page 7 - research similar products |  |  |  | 11 |  |  |  | 1 | 1. finish login page 2. finish register page |  |  | 3 - implement login page 3 - implement register page | 8
7 | 10/19-10/25 |  | 32 |  | 0 - learning javascript 0 - learning JQuery 3 - change style of product page 3 - implement password hiden/show effect 3 - add home button in all pages 3 - change style of product list page 3 - implement fly to cart effects 3 - implement wrong email password format tips effect 3 - add more product and info to product list page 5 - send reminders to teammates 5 - merge code with backend 7 - prepare presentation | 3 |  |  | 20 |  | 4 |  | 5 | 1. finish product page 2. implement fly to cart effect 3. implement hiden/show password effect 4. implement email/password format tips pop effect | 1. fly to cart ending points are not all correct 2. hiden/show password code redundancy 3. navigation layout inappropriate in small window | 1. check the ending point path again 2. try to include them in a loop 3. learn more about layout | 1. implement cart shake effect 2. change the size of "add to cart" button 3. fix the issues 4. learn Jinja | 15

## Hussain Alibrahim
Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/09-16/20 | 9.5 | 9.5 | 1 | 0 - relearning git's system, preparing in case of needed assistance in git 0 - learn django since it is a new to me, never worked on it before 3 - set up git for lab1 as well as future work 0 - keeping up to date with needed front-end knowledge (javascript, html, etc.) | 9 |  |  | 0.5 |  |  |  |  | 1. Set up git, commit a test message on git 2. Participate in Iteration 0 presentation 3. ability to provide assistance as config leader in short notice | 1. unclear class assignments which cause confusion 2. Never worked with Django before so it's difficult to get used to 3. creating a git info document is really time consuming | 1. Will make sure to note down class assignments in next class and keep my teammates up to date on them at all times 2. Will dedicate every week to making sure I learn Django in and out so I don't lag behind 3. Will keep updating my Git Info document in case an issue I didn't anticipate pops up. New knowledge is better than thinking that you have all knowledge. | 1. Cooperate with teammate on how we should begin the front end and make sure it goes as smoothly as can be. 2. Continue my django learning process as well as my git info database 3. Make some test vues/pages to make sure I test my concepts before I implement into our official project.
2 | 09/16-24/20 | 11 | 10 | 1 | 1- establishing guidelines for git commit system 7- setting up adobe for designing the pages 2 - Desiging logo 3- starting static pages for webapp 7. prepare presentation |  | 0.5 | 0.5 | 5 |  |  |  | 4 | 1. Finished Logo 2. Commit guidelines established 3. Adobe programs available for design purposes | 1. Time Constraits from other classes/assignments 2. preparing moving into US, so more time lost 3. still need to test commit guidelines to see the issues | 1. I will be moving on the 2nd of october, so time will be short till I move in 2. Still need to test guidelines 3. worked out schedule for other classes which gives me time for working on this project | 1. Continue working on static pages for webapp 2. transition into dynamic site 3. Prepare for database integration | 10
3

## Bhavesh Tadikonda
Lead Roles: Backup Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/13 | 13 | 10 | 1 | 0 - learn Flask microservice, MongoDB and Third party Integration to webapp. 5 - assign tasks to subteams, actively send reminders to team members. 0 - Leaning Graphql,GPRC, RESTful figuring out which will be best API style. | 11 |  |  |  |  | 2 |  |  | 1. API design using RESTful. | New to designning Scalable API. | Learned more about different types of API's. can be implemented. |  | 13
1 | 09/14-09/20 | 14 | 13 | 1 | 0 - learn Flask and MongoDB 1 - analyzing functional requriments,non functionalities requriments and HLD design 2 - designing Payment functionalites | 4 | 3 | 7 | [5 empty] | 1. Designing the High level design | Not familiar with payment gateways API's and High level design | Learn more about Payment API's and CAP theorem for HLD |  | 14
1 | 09/20-09/24 | 14 | 11 | 3 | 0 - Learned how to host the application on the public serverices, Like AWS,netlify and github hosting. 2 - Designed database schemas with attributes in the each collections. 5 - Explained OAuth authorziation code flow to Ming. Had a clear conversation with backend team,explained how application will work and assigned prioritization for each task. 1- analysed what functionality and actions need to be present in each page of application. after each page,which page it should be redirected. | 3 | 4 | 4 |  |  | 3 |  |  | 1. write endpoints of the applications, architecture and database attributes in SPPB document. 2. Prepared Powerpoint presentation for iteration 0, Prepared endpoints of the application slide and Introduction slide. |  |  |  | 14
1 | 09/25-10/2 | 14 | 12 | 2 | 2- Designed the authorization code flow using google login 5- cordinate with team members, checking the progress on tasks 3 - Partially implementation was started. 0 - Deploying the application, which cloud service is preferrable. | 5 |  | 4 | 3 |  | 2 |  |  | 1. Preparing for iteration 1 |  |  |  | 14
1 | 10/2-10/9 | 13 | 12 | 1 | 3 - Implemented google login for the application 5 - cordinate with team members, checking the progress on tasks 4 - testing the google login for the web app |  |  |  | 10 | 2 | 1 | [6 empty] | 14
1 | 10/9-10/16 | 14 | 13 | 1 | 2 - Designing the Payment page with Stripe checkout and working on design for Home page with only featured products(static content) 5- Communicated with team members and conducting meetings |  |  | 13 |  |  | 1 | [6 empty] | 14
1 | 10/16-10/22 | 16 | 15 | 1 | [13 empty] | 14